## Attendant List
Project Schedule
Batch | 2/2019
Mentor | Huỳnh Văn Thông
Duration | 21/06/2019 - 30/09/2019
No | Name | Start Date | End Date | Course Name | Status | Archivement | Note
1 | Đỗ Thành Nhân | 2019-06-21 | 2019-09-30 | ReactJS | On-Going |  | Internship
2 | Nguyễn Hữu Tài | 2019-06-21 | 2019-09-30 | ReactJS | On-Going |  | Internship
3 | Cao Anh Quốc | 2019-06-21 | 2019-09-30 | ReactJS | On-Going |  | Internship
4 | Phan Thanh Hoài | 2019-06-21 | 2019-09-30 | ReactJS | On-Going |  | Internship

## Enroll- Course X (hidden)
No | Name | Subject | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | Archivement | Note
1 | Nguyễn Van A | #REF! | x | [24 empty] | Create a website with header, title, body, Img tag…

## Sheet1 (hidden)
No | Name | Subject
1 | Nguyễn Van A

## Course Name2 (hidden)
COURSE NAME From ___ To_____
No. | Training Outline | Content | Duration |  | Objectives | Training Method | Start date | Finish date | Progress | Notes
|  |  | Plan | Actual
After 2 weeks | Presentation | Content
After 2 weeks | Presentation | Content
After 2 weeks | Presentation | Content
Finish course | Presentation | Content

## React JS
Reactjs Training Schedule
No. | Training Outline | Content | Duration (h) |  | Objectives | Training Method | Start date | Finish date | Progress | Notes
|  |  | Plan | Actual
1 | Introduce | Introduce about Javascript, Reactjs | 4 |  | Have the overview of Reactjs | Mentor | 2019-07-24 | 2019-07-24 | 100/100
2 | GIT | Basic GIT usage | 8 |  |  | Seft-training | 2019-07-24 | 2019-07-24 | 70/100 | https://confluence.atlassian.com/bitbucketserver/basic-git-commands-776639767.html
3 | Javascript(>ES5) | Javascript Syntax | 8 |  | Have a knowledge about Javascript | Seft-training | 2019-06-25 | 2019-06-25 | 100/100 | https://www.w3schools.com/js/default.asp http://es6-features.org/#Constants https://www.w3schools.com/js/js_syntax.asp https://www.w3schools.com/js/js_es6.asp
|  | JS Objects | 8 |  |  |  | 2019-06-25 | 2019-06-25 | 100/100 | https://www.w3schools.com/js/js_object_definition.asp
|  | JS Functions | 8 |  |  |  | 2019-06-25 | 2019-06-25 | 100/100 | https://www.w3schools.com/js/js_function_call.asp
|  | Local Storage, Session Storage, Cookie | 8 |  |  |  | 2019-06-26 | 2019-06-28 | 100/100 | https://scotch.io/@PratyushB/local-storage-vs-session-storage-vs-cookie https://viblo.asia/p/local-storage-session-storage-va-cookie-ORNZqN3bl0n
|  | JS HTML DOM | 8 |  |  |  | 2019-06-26 | 2019-06-28 | 100/100 | https://www.w3schools.com/js/js_htmldom.asp
|  | Presentation 1: Javascript, GIT | 2
4 | Reactjs | JSX | 8 |  | Have a knowledge about Reactjs |  | 2019-07-01 | 2019-07-01 | 100/100 | https://reactjs.org/docs/introducing-jsx.html
|  | Rendering Elements | 8 |  |  |  | 2019-07-02 | 2019-07-03 | 100/100 | https://reactjs.org/docs/rendering-elements.html
|  | Components and Props | 8 |  |  |  | 2019-07-02 | 2019-07-03 | 100/100 | https://reactjs.org/docs/components-and-props.html
|  | State and Lifecycle | 8 |  |  |  | 2019-07-02 | 2019-07-03 | 80/100 | https://reactjs.org/docs/state-and-lifecycle.html
|  | Handling Events | 8 |  |  |  | 2019-07-04 | 2019-07-04 | 100/100 | https://reactjs.org/docs/handling-events.html
|  | Conditional Rendering | 8 |  |  |  | 2019-07-05 | 2019-07-05 | 80/100 | https://reactjs.org/docs/conditional-rendering.html
|  | Lists and Keys | 8 |  |  |  | 2019-07-08 | 2019-07-08 | 90/100 | https://reactjs.org/docs/lists-and-keys.html
|  | Forms & Validate | 16 |  |  |  | 2019-07-08 | 2019-07-08 | 100/100 | https://reactjs.org/docs/forms.html
|  | Lifting State Up | 16 |  |  |  | 2019-07-09 | 2019-07-09 | 80/100 | https://reactjs.org/docs/lifting-state-up.html
|  | Composition vs Inheritance | 16 |  |  |  | 2019-07-09 | 2019-07-09 | 80/100 | https://reactjs.org/docs/composition-vs-inheritance.html
|  | Communication between parent and child | 20 |  |  |  | 2019-07-10 | 2019-07-10 | 100/100 | https://anthonymineo.com/simple-child-to-parent-communication-in-react/
|  | Forwarding Refs | 20 |  |  |  | 2019-07-11 | 11/072/109 | 80/100 | https://reactjs.org/docs/forwarding-refs.html
|  | Presentation 2: React JS | 2
5 | React-redux | - Init redux store - Create actions, reducers, services - Integrate redux to reactjs | 50 |  | Apply redux to reactjs |  |  |  |  | https://viblo.asia/p/bat-dau-voi-reactjs-phan-2-1Je5EMGA5nL
|  | Presentation 3: React-redux + Demo | 2
6 | Demo | Create a demo with what has been trained Eg: Create a workshop include: - Admin page: manage product (add/edit/delete) - Home page: show the product - Product page: to show the detail of the product - Register page - Login page, ..... | 180 |  | Understand and apply the knowledge in the product | Seft-training |  |  |  | The mentor needs to update after receiving the requirement
7 | Final Report | Presentation of trained knowledge and demo | 4 |  | Understand and be able to work with Reactjs | Seft-training
|  | Sum | 400 |  | hours
|  |  | 13.3333 |  | weeks (Count 6hours/day,because Interns will join other training courses (English, Softskill))

## Q&A
No | Questions | Answer | Trainer

## Temp (hidden)
Seft-training
Mentor
Sharing meeting